## Warp It Delivery Plan Template
Reuse programe Implementation chart - to be used in conjunction with Embed guide (see www.getwarpit.com/embedguide).
Implementation team: | PROJECT LEAD | SUSTAINABILITY LEAD | ESTATES LEAD | PROCUREMENT LEAD
Email contact
Phone contact
Vision | Guide here | Set the vision for the project
Goals: | Guide here | Set the goals of the project |  |  |  |  | In the time periods you could put Weeks or months depending on how long you factor the roll out of the project. You can also use the spaces to colour code or to add dates. Depending on your desired way of using the chart.
Here you can number the tasks in order to the bottom, within each section or bespoke to your requirements
[5 empty] | Time period 1 (Eg day/ week / month) |  |  |  | Time period |  |  |  | Time period 3 |  |  |  | Time period 4
Task Number | Section | Activity | Supporting Document | Responsible party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Pre set up | Attend orientation session | Book your slot here
|  | Get buy in- stakeholder meeting | Build your implementation team
|  | Get PUBLIC backing from the top! | Launch Template
|  | 3rd party trades- legal agreement | The agreement can be found in Admin>Customise messages> Legal
| Setting up | Edit company account profile | Admin>Settings>Edit profile
|  | Meet your comms team | Plan your comms.
|  | Add yourself as a standard user | Go to your company homepage> Register>Fill in details
|  | Set up controls in settings | Admin>Settings>Control….
|  | Customise the reporting factors | Admin>Settings>Customise reports
|  | Customise the messages | Admin>Customise Messages
| Mini Pilot | Email Warp It implementation team | Email templates here.
|  | Check IT security status of Warp It | Send this info to ensure emails get through.
|  | Encourage trading of first items | You can send a message via the system. Admin>Members>Email
|  | Schedule a meeting of mini pilot members | Put it in calendar for 2 weeks after initial message. Send invtes.
|  | Bulk Upload | Populate your system before full launch. Bulk upload guide here
| Release into the wild | Launch communications meeting | Templates here. Please also discuss other methods of communications.
|  | Intranet content | Content here
|  | Add senior managers and other staff (optional) | This can be done in Admin> Members>Add members
|  | Communicate to staff through different channels | Quick and easy actions
|  | Cascade the news through management structure | Guide here.
| Post launch | Deliver User training (Warp It provide or internal)
|  | Tell staff how they are doing | Templates
|  | Incentive encouragement (optional but very effective) | Guide here.
|  | Building an external network | Guide here.
| Reviews | Increase participation with regular communication | Communications ideas
|  | Review of embed procedure and performance | How did you do? What worked? What did not work?
|  | Get feedback from staff | You could do a survey.
|  | Review policy & set a reuse target. | Policy guides here.